## Arms Sale Backlog FINAL
Date of Sale | Capability Sold | Dollar Value (In Millions) | Weapon Category | Note | Status as of November 1, 2023 | DSCA Sale Link
2020-10-21 | HIMARS | 436.1 | Asymmetric | 11 HIMARS launchers, 64 ATACMS missiles, various support equipment. | The HIMARS sale was increased from 11 to 29 launchers in 2022. Reporting from May 2023 indicated that Taiwan would receive its first HIMARS launchers in 2026 but did not specify a date for when all launchers will be delivered: https://focustaiwan.tw/politics/202305100015 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-15
2020-10-26 | Harpoon Coastal Defense System | 2370 | Asymmetric | 100 ground-based launchers, 25 radar trucks, and 400 Harpoon missiles. | Reporting from April 2023 indicated March 2029 as completion date for the 400 Harpoon missiles: https://www.reuters.com/world/asia-pacific/taiwan-buy-400-us-anti-ship-missiles-face-china-threat-bloomberg-news-2023-04-17/. In March 2022, a contract was finalized for delivery of the launchers, radar, and training equipment, which is expected to be completed in December 2028: https://www.defense.gov/News/Contracts/Contract/Article/2952403/ | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-17
2020-11-03 | MQ-9B Unmanned Aircraft | 600 | Asymmetric | 4 MQ-9B Sea Guardian drones and associated sensors and support equipment | Reporting from May 2023 indicated that delivery is expected in May 2025: https://www.airforce-technology.com/news/taiwan-acquires-four-mq-9b-skyguardian-uas/. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-18
2020-12-07 | Field Information Communications System | 280 | Asymmetric | Battlefield communication system. | Reporting from March 2022 indicated delivery by September 2025: https://www.taiwannews.com.tw/en/news/4469659 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-19
2022-09-02 | Air-Launched Harpoon Missiles | 355 | Asymmetric | Does not appear in SIPRI dataset. 60 AGM-84-L-1 air launched Harpoons plus associated spare parts and support equipment. | Report from January 2023 indicated that these missiles will be delivered by 2030: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-agm
2022-12-28 | Volcano Anti-Tank Mining System | 180 | Asymmetric | Does not appear in SIPRI dataset. Unspecified number of vehicle-launched anti-tank mine laying systems and related support vehicles. | Reporting from June 2023 indicated delivery before the end of 2029: https://focustaiwan.tw/politics/202306290007 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-27
2017-06-29 | AGM-154C Joint Standoff Weapon | 185.5 | Munition | 56 AGM-154C JSOW Air-to-Ground Missiles plus various spares and support services. | Reporting from September 2022 said delivery of the missiles was "delayed" but there was an expectation for delivery in 2023. There has been no update to confirm delivery in 2023 yet: https://web.archive.org/web/20220907120055/https://focustaiwan.tw/politics/202209050011 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-1
2017-06-29 | Mk 48 Heavyweight Torpedoes | 250 | Munition | 46 announced in the DCSA sale. SIPRI dataset shows 28 torpedoes in a 2018 sale and 18 in 2020. | Reporting from May 2023 indicated delivery of 46 Mk-48 torpedoes would take place in 2025: https://www.taipeitimes.com/News/taiwan/archives/2023/05/07/2003799314 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-3
2017-06-29 | Lightweight Torpedoes and Conversion Kits | 175 | Munition | Does not appear in SIPRI dataset. For upgrade of 168 Mk-46 Mod 5 Torpedoes to the Mk-54 Lightweight Torpedo configuration. | No readily available reporting on this sale. Based on timing, composition, and size, it will most likely be delivered soon if it hasn't already. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-4
2020-05-20 | Mk 48 Heavyweight Torpedoes | 180 | Munition | 2017 arms sale for 46 torpedoes was later reduced. This 2020 sale corrects for that reduction and brings the total Mk-48 number back to 46. | Reporting from May 2023 indicated delivery of 46 Mk-48 torpedoes would take place in 2025: https://www.taipeitimes.com/News/taiwan/archives/2023/05/07/2003799314 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-12
2020-10-21 | AGM-84H SLAM-ER Missile | 1008 | Munition | Does not appear in the SIPRI dataset. 135 missiles plus some training munitions, spare parts, and test equipment. | Reporting from January 2023 indicated a "large quantity of unnamed long-range weapons" for the F-16V will be delivered by 2030. The SLAM-ER was not confirmed to be part of this package, but it is suspected to be part of the package: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-16
2022-09-02 | AIM-9X Block II Missiles | 85.6 | Munition | Does not appear in SIPRI dataset. 100 AIM-9X sidewider missiles and four guidance unit kits. | Report from January 2023 indicated that these missiles will be delivered by 2030: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-aim
2023-03-01 | F-16 Munitions | 619 | Munition | Does not appear in SIPRI dataset. AGM-88B HARMs and AIM-120-C-8 AMRAAMs are most numerous missiles at 100 and 200, repsectively. | These missiles might be part of a large sale of F-16 munitions that should arrive in Taiwan by the end of 2030. Some of the munitions mentioned for the 2030 delivery match with the munitions in the DSCA sale, but not all of the munitions: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-f-16
2023-06-29 | 30mm Ammunition | 332.2 | Munition | Does not appear in SIPRI dataset. Covers various types of 30mm ammunition. | As of November 1, 2023 there was no additional reporting on this arms sale to provide an expected delivery date. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-29
2015-12-16 | MK 15 Phalanx CIWS | 416 | Traditional | Delivery begun but not completed according to SIPRI dataset. Subsystem of a large surface warship, which would be considered a traditional capability. | 11 of 13 systems delivered according to March 2023 press reports: https://www.taiwannews.com.tw/en/news/4852295 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-mk-15
2017-06-29 | AN/SLQ-32 Electronic Warfare System for Keelung-class destroyer | 80 | Traditional | Does not appear in SIPRI dataset. Subsystem of a large surface warship, which would be considered a traditional capability. | Reporting from December 2018 indicated this sale was expected to be completed "by 2023" but does not specify when: https://www.taipeitimes.com/News/front/archives/2018/12/10/2003705831 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-2
2019-07-08 | M1A2T Abrams Tanks | 2000 | Traditional | 108 tanks plus related ammunition, sensors, and other support equipment. | Reporting from August 2023 indicated Taiwan will begin receiving a shipment of 38 tanks in 2024, with delivery expected to be complete in 2026: https://www.thedefensepost.com/2023/08/23/taiwan-abrams-tanks-us/ | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-9
2019-08-20 | F-16C/D Block 70 | 8000 | Traditional | 66 aircraft plus various avionics, spare engines, and other supporting equipment. | Reporting from May 2023 indicated Taiwan will receive all 66 aircraft by 2026: https://www.reuters.com/business/aerospace-defense/taiwan-says-software-problems-delaying-new-f-16-deliveries-2023-05-25/ | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-11
2020-10-21 | MS-110 Recce Pods | 367.2 | Traditional | Reconnaissance pod for manned aircraft. | Reporting from August 2021 indicated delivery of six MS-110 pods is expected by March 2029: https://web.archive.org/web/20210728100225/https://focustaiwan.tw/politics/202107280015 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-14
2021-08-04 | M109A6 Paladin Self-Propelled Howitzer | 750 | Traditional | 40 Paladin howitzers, plus various support behicles and guidance kits for artillery rounds. | Reporting from May 2023 indiciated that delivery of the howitzers was delayed from 2023 to 2026: https://www.reuters.com/world/asia-pacific/taiwan-considers-alternatives-after-us-informs-howitzer-delay-2022-05-02/. More recent reporting from Taiwan indicated that Taiwan had cancelled the sale and opted to purchase more HIMARs, but it is unclear if the howitzers were completely cancelled or the relative balance of HIMARS to howitzers was adjusted. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-20
2023-08-23 | F-16 IRST Systems | 500 | Traditional | Does not appear in SIPRI dataset. Infrared Search and Track systems for use on F-16 aircraft. | As of November 1, 2023 there was no additional reporting on this arms sale to provide an expected delivery date. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-30
Backlog Total | 19169.6
Asymmetric Total | 4221.1
Munition Total | 2835.3
Traditional Total | 12113.2

## Maintenance UPDATED &comparison
Date of Sale | Capability Sold | Dollar Value (In Millions) | Weapon Category | Description | Administration | DSCA Sale Link
2017-06-29 | Surveillance Radar Program Support | 400 | Traditional | Operation and maintenance support for a missile and air defense early warning radar. Classified as "Traditional" due to the radar's immobility and vulnerability to attack. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-6
2018-09-24 | Foreign Military Sales Order | 330 | Traditional | Replenishment of standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-tecro
2019-04-15 | CONUS Based F-16 Training | 500 | Traditional | Continuation of a pilot training program and maintanence/logistics support for Taiwanese F-16s at Luke Air Force Base in Arizona. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-8
2020-07-09 | PAC-3 Repair and Recertification | 620 | Asymmetric | Replacement of expiring limited life components, certification testing, replenishment of missile spare parts, seeker spares pool, and other various items related to sustainment of the PAC-3. Classified as "Asymmetric" due to PAC-3s mobility and ability to shoot down aircraft. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-13
2022-02-07 | IESP and FSP Support | 100 | Asymmetric | Equipment and services for five years to support Taiwan's participation in the Patriot International Engineering Services Program and Field Surveillance Program. Funds will sustain, maintain, and improve Taiwan's Patriot air defense systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-21
2022-04-05 | Contractor Technical Assistance, Patriot | 95 | Asymmetric | Support for training, fielding, operations, and sustainment of the Patriot system. This support is supposed to improve the readiness of Taiwan's Patriot systems and ensure readiness for operations. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-22
2022-06-08 | Ship Spare Parts | 120 | Traditional | Spare and repair parts for manned surface warships, from US Navy stocks and approved US Navy vendors. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-ship
2022-07-15 | Blanket Order Contractor Technical Support | 108 | Traditional | Spare and repair parts for tanks and other ground combat vehicles, small arms, and other capabilities. Classified as "Traditional" because tanks are a traditional capability, but the scope of this sale means it could include support for asymmetric systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-23
2022-09-02 | Surveillance Radar Program Support | 665.4 | Traditional | Operation and maintenance support for a missile and air defense early warning radar. Classified as "Traditional" due to the radar's immobility and vulnerability to attack. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-24
2022-12-06 | Aircraft Spare Parts, Standard | 330 | Traditional | Replenishment of standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-26
2022-12-06 | Aircraft Spare Parts, Non-Standard | 98 | Traditional | Replenishment of non-standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-25
2023-06-29 | Foreign Military Sales Order II | 108 | Asymmetric | Spare and repair parts for wheeled vehicles, small arms, and other weapons systems. Coded as "Asymmetric" because many of Taiwan's asymmetric weapons systems (e.g. ground-based anti-ship and anti-air missiles, missile defense systems, mobile command and control systems) use wheeled vehicles, but the scope of the sale means it could include support for traditional systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-28
Maintenance Total | 3474
Asymmetric Maintenance Total | 923
Traditional Maintenance Total | 2551
| Asymmetric | Traditional
Trump | 620 | 1230
Biden | 303 | 1321.4

## Trump v Biden Total
Date of Sale | Capability Sold | Dollar Value (In Millions) | Weapon Category
TRUMP
2017-06-29 | AGM-154C Joint Standoff Weapon | 185.5 | Munition
2017-06-29 | Mk 48 Heavyweight Torpedoes | 250 | Munition
2017-06-29 | AGM-88B High Speed Anti-Radiation Missile (HARM) | 147.5 | Munition | Delivered in 2023
2017-06-29 | Lightweight Torpedoes and Conversion Kits | 175 | Munition
2017-06-29 | AN/SLQ-32 Electronic Warfare System for Keelung-class destroyer | 80 | Traditional
2017-06-29 | Surveillance Radar Program Support | 400 | Maintenance
2018-09-24 | Foreign Military Sales Order | 330 | Maintenance
2019-04-15 | CONUS Based F-16 Training | 500 | Maintenance
2019-07-08 | Stinger MANPAD | 223.56 | Asymmetric | Delivered in 2023
2019-07-08 | M1A2T Abrams Tanks | 2000 | Traditional
2019-08-20 | F-16C/D Block 70 | 8000 | Traditional
2020-05-20 | Mk 48 Heavyweight Torpedoes | 180 | Munition
2020-07-09 | PAC-3 Repair and Recertification | 620 | Maintenance
2020-10-21 | HIMARS | 436.1 | Asymmetric
2020-10-21 | AGM-84H SLAM-ER Missile | 1008 | Munition
2020-10-21 | MS-110 Recce Pods | 367.2 | Traditional
2020-10-26 | Harpoon Coastal Defense System | 2370 | Asymmetric
2020-11-03 | MQ-9B Unmanned Aircraft | 600 | Asymmetric
2020-12-07 | Field Information Communications System | 280 | Asymmetric
2017-06-19 | SM-2 and Components | 125 | Munition | Delivered in 2022
Asymmetric Total | 3909.66
Traditional Total | 10447.2
Munitions Total | 2071
Maintenance Total | 1850
BIDEN
2021-08-04 | M109A6 Paladin Self-Propelled Howitzer | 750 | Traditional
2022-02-07 | IESP and FSP Support | 100 | Maintenance
2022-04-05 | Contractor Technical Assistance, Patriot | 95 | Maintenance
2022-06-08 | Ship Spare Parts | 120 | Maintenance
2022-07-15 | Blanket Order Contractor Technical Support | 108 | Maintenance
2022-09-02 | Air-Launched Harpoon Missiles | 355 | Asymmetric
2022-09-02 | AIM-9X Block II Missiles | 85.6 | Munition
2022-09-02 | Surveillance Radar Program Support | 665.4 | Maintenance
2022-12-06 | Aircraft Spare Parts, Standard | 330 | Maintenance
2022-12-06 | Aircraft Spare Parts, Non-Standard | 98 | Maintenance
2022-12-28 | Volcano Anti-Tank Mining System | 180 | Asymmetric
2023-03-01 | F-16 Munitions | 619 | Munition
2023-06-29 | 30mm Ammunition | 332.2 | Munition
2023-06-29 | Foreign Military Sales Order II | 108 | Maintenance
2023-08-23 | F-16 IRST Systems | 500 | Traditional
Asymmetric Total | 535
Traditional Total | 1250
Munitions Total | 1036.8
Maintenance Total | 1624.4
Column1 | Asymmetric | Traditional | Munitions | Maintenance
Trump | 3909.66 | 10447.2 | 2071 | 1850
Biden | 535 | 1250 | 1036 | 1624.4