## Arms Sale Backlog FINAL
Date of Sale | Capability Sold | Dollar Value (In Millions) | Weapon Category | Note | Status as of April 30, 2024 | DSCA Sale Link
2017-06-29 | AGM-154C Joint Standoff Weapon | 185.5 | Munition | 56 AGM-154C JSOW Air-to-Ground Missiles plus various spares and support services. | Reporting from February 2024 indicated a contract signed with RTX (formerly Ratheon) for 50 AGM-154Cs for $68.4 million to be delivered by March 2028: https://www.taipeitimes.com/News/front/archives/2024/02/05/2003813098 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-1
2017-06-29 | Mk 48 Heavyweight Torpedoes | 250 | Munition | 46 announced in the DCSA sale. SIPRI dataset shows 28 torpedoes in a 2018 sale and 18 in 2020. | Reporting from May 2023 indicated delivery of 46 Mk-48 torpedoes would take place in 2025: https://www.taipeitimes.com/News/taiwan/archives/2023/05/07/2003799314. SIPRI 2024 data indicates delivery of 5 torpedoes in 2023, with full delivery planned by 2026. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-3
2019-07-08 | M1A2T Abrams Tanks | 2000 | Traditional | 108 tanks plus related ammunition, sensors, and other support equipment. | Reporting from August 2023 indicated Taiwan will begin receiving a shipment of 38 tanks in 2024, with delivery expected to be complete in 2026: https://www.thedefensepost.com/2023/08/23/taiwan-abrams-tanks-us/. SIPRI Arms Transfer Database data from March 2024 indicates final delivery expected in 2026. March 2024 SIPRI data indicates 2 tanks were delivered in 2022, likely for initial familiarization. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-9
2019-07-08 | Stinger Missiles | 223 | Asymmetric | 250 Block 1-92F MANPAD Stinger missiles as well as supporting equipment and gripstocks. | Reporting from early February 2024 indicated that a first batch of these Stingers were delivered sometime in 2023. Final delivery expected sometime in 2024:https://www.crowrivermedia.com/national/news/stinger-missiles-delivered-to-taiwan-last-year-say-sources---taiwanplus-news/video_36aacc4f-9261-53a5-9dc1-1149ecefb04c.html#:~:text=The%20U.S.%20delivered%20part%20of,sources%20familiar%20with%20the%20matter. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-10
2019-07-08 | TOW-2B Missiles | 241 | Asymmetric | 1,240 TOW 2B mssiles, 58 Improved Target Acqusition Systems 100 Humvees | The 1,240 TOW missiles were an addition to an earlier, December 2015 sale of similar missiles. Not includedin earlier versions of the dataset due to lack of information on the modification in older sources of data. SIPRI 2024 update mentions that deliveries of the missiles should begin in 2024. | https://www.govinfo.gov/content/pkg/CREC-2019-07-08/pdf/CREC-2019-07-08.pdf
2019-08-20 | F-16C/D Block 70 | 8000 | Traditional | 66 aircraft plus various avionics, spare engines, and other supporting equipment. | Reporting from May 2023 indicated Taiwan will receive all 66 aircraft by 2026: https://www.reuters.com/business/aerospace-defense/taiwan-says-software-problems-delaying-new-f-16-deliveries-2023-05-25/ | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-11
2020-05-20 | Mk 48 Heavyweight Torpedoes | 180 | Munition | 2017 arms sale for 46 torpedoes was later reduced. This 2020 sale corrects for that reduction and brings the total Mk-48 number back to 46. | Reporting from May 2023 indicated delivery of 46 Mk-48 torpedoes would take place in 2025: https://www.taipeitimes.com/News/taiwan/archives/2023/05/07/2003799314. SIPRI 2024 data indicates delivery of 5 torpedoes in 2023, with full delivery planned by 2026. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-12
2020-10-21 | HIMARS | 436.1 | Asymmetric | 11 HIMARS launchers, 64 ATACMS missiles, various support equipment. | The HIMARS sale was increased from 11 to 29 launchers in 2022. Taiwan reporting from May 2023 citing MND sources said that delivery of first 11 HIMARS would be complete by 2025, while delivery of the 18 additional launchers would be completed in 2026: https://www.taiwannews.com.tw/en/news/4883328 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-15
2020-10-21 | AGM-84H SLAM-ER Missile | 1008 | Munition | 135 missiles plus some training munitions, spare parts, and test equipment. | Reporting from January 2023 indicated a "large quantity of unnamed long-range weapons" for the F-16V will be delivered by 2030. The SLAM-ER was not confirmed to be part of this package, but it is suspected to be part of the package: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-16
2020-10-21 | MS-110 Recce Pods | 367.2 | Traditional | Reconnaissance pod for manned aircraft. | Contract announcement from December 22, 2021 indicates a completion date of November 30, 2025, https://www.defense.gov/News/Contracts/Contract/Article/2882869/. According to March 2024 SIPRI data, 3 of 6 pods have been delivered as of the end of 2023, with full delivery occurring probably by 2025. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-14
2020-10-26 | Harpoon Coastal Defense System | 2370 | Asymmetric | 100 ground-based launchers, 25 radar trucks, and 400 Harpoon missiles. | In March 2022, a contract was finalized for delivery of the launchers, radar, and training equipment, which is expected to be completed in December 2028: https://www.defense.gov/News/Contracts/Contract/Article/2952403/. An April 2023 contract award announcement for 400 Harpoon missiles, which does not mention Taiwan by name but has the correct number of missiles and support equipment, puts delivery as March 2029: https://www.defense.gov/News/Contracts/Contract/Article/3356129/ | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-17
2020-11-03 | MQ-9B Unmanned Aircraft | 600 | Asymmetric | 4 MQ-9B Sea Guardian drones and associated sensors and support equipment | Contract announcement from May 1, 2023 indicates delivery of four MQ-9Bs and two ground stations will be completed on May 5, 2025: https://www.defense.gov/News/Contracts/Contract/Article/3380162/. Asecond contract award announcement from March 12, 2024 indicates final delivery in August 2027. A reporter from Taiwan's Central News Agency confirmed that the two contracts are for the purchase of 4 drones and 2 ground stations, meaning the purchase was divided across two contracts. https://www.defense.gov/News/Contracts/Contract/Article/3704846/. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-18
2020-12-07 | Field Information Communications System | 280 | Asymmetric | Battlefield communication system. | Reporting from March 2022 indicated delivery sometime in 2025: https://www.taipeitimes.com/News/taiwan/archives/2022/03/12/2003774639 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-19
2022-09-02 | Air-Launched Harpoon Missiles | 355 | Asymmetric | 60 AGM-84-L-1 air launched Harpoons plus associated spare parts and support equipment. | Report from January 2023 indicated that these missiles will be delivered by 2030: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-agm
2022-09-02 | AIM-9X Block II Missiles | 86 | Munition | 100 AIM-9X sidewider missiles and four guidance unit kits. | Report from January 2023 indicated that these missiles will be delivered by 2030: https://www.taiwannews.com.tw/en/news/4777553. SIPRI March 2024 data also suggests delivery planned by 2030. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-aim
2022-12-05 | PAC-3 MSE Interceptors | 882 | Asymmetric | 100 PAC-3 MSE Interceptors. Modification to a January 2010 arms sale of Patriot batteries and interceptors to Taiwan. Not reported in DSCA data. | Taiwan News report from January 2024 quotes MND saying deliveries to occur in batches between 2025 and 2026: https://www.taiwannews.com.tw/en/news/5079542 | https://www.govinfo.gov/content/pkg/CREC-2022-12-05/pdf/CREC-2022-12-05.pdf
2022-12-05 | HIMARS | 520 | Asymmetric | DSCA notified Congress of a purchase of 18 additional HIMARS in December 2022, plus 144 GMLRS pods, 20 ATACMS pods, and support vehicles. | The HIMARS sale was increased from 11 to 29 launchers in 2022. Taiwan reporting from May 2023 citing MND sources said that delivery of first 11 HIMARS would be complete by 2025, while delivery of the 18 additional launchers would be completed in 2026: https://www.taiwannews.com.tw/en/news/4883328. SIPRI March 2024 data indicates the US also sold 864 GMLRS rockets as part of the plus-up. Unclear if GMLRS sale is individual rockets or pods (6 rockets per pod). | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.govinfo.gov/content/pkg/CREC-2022-12-05/pdf/CREC-2022-12-05.pdf
2022-12-28 | Volcano Anti-Tank Mining System | 180 | Asymmetric | Does not appear in SIPRI dataset. Unspecified number of vehicle-launched anti-tank mine laying systems and related support vehicles. | Reporting from June 2023 indicated delivery before the end of 2029: https://focustaiwan.tw/politics/202306290007 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-27
2023-03-01 | F-16 Munitions | 619 | Munition | AGM-88B HARMs and AIM-120-C-8 AMRAAMs are most numerous missiles at 100 and 200, respectively. | These missiles might be part of a large sale of F-16 munitions that should arrive in Taiwan by the end of 2030. Some of the munitions mentioned for the 2030 delivery match with the munitions in the DSCA sale, but not all of the munitions: https://www.taiwannews.com.tw/en/news/4777553 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-f-16
2023-06-29 | 30mm Ammunition | 332.2 | Munition | Covers various types of 30mm ammunition. | As of April 30, 2024 there was no additional reporting on this arms sale to provide an expected delivery date. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-29
2023-08-23 | F-16 IRST Systems | 500 | Traditional | Infrared Search and Track systems for use on F-16 aircraft. | As of April 30, 2024 there was no additional reporting on this arms sale to provide an expected delivery date. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-30
2024-02-21 | Taiwan Advanced Tactical Data Link System Upgrade | 75 | Asymmetric | Sale of GPS receivers, communication equipment, engineering and technical services, and other items to upgrade military communication systems. | No updates beyond announcement of initial sale. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-32
Backlog Total, March 2024 | 19170
Asymmetric Total, March 2024 | 5642
Munition Total, March 2024 | 2661
Traditional Total, March 2024 | 10867
Backlog Total, April 2024 | 19690 | $520 increase
Asymmetric Total, April 2024 | 6162 | $520 increase
Munition Total, April 2024 | 2661 | No change
Traditional Total, April 2024 | 10867 | No change

## Maintenance
Date of Sale | Capability Sold | Dollar Value (In Millions) | Weapon Category | Description | Administration | DSCA Sale Link
2017-06-29 | Surveillance Radar Program Support | 400 | Traditional | Operation and maintenance support for a missile and air defense early warning radar. Classified as "Traditional" due to the radar's immobility and vulnerability to attack. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-tecro-united-6
2018-09-24 | Foreign Military Sales Order | 330 | Traditional | Replenishment of standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-tecro
2019-04-15 | CONUS Based F-16 Training | 500 | Traditional | Continuation of a pilot training program and maintanence/logistics support for Taiwanese F-16s at Luke Air Force Base in Arizona. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-8
2020-07-09 | PAC-3 Repair and Recertification | 620 | Asymmetric | Replacement of expiring limited life components, certification testing, replenishment of missile spare parts, seeker spares pool, and other various items related to sustainment of the PAC-3. Classified as "Asymmetric" due to PAC-3s mobility and ability to shoot down aircraft. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-13
2022-02-07 | IESP and FSP Support | 100 | Asymmetric | Equipment and services for five years to support Taiwan's participation in the Patriot International Engineering Services Program and Field Surveillance Program. Funds will sustain, maintain, and improve Taiwan's Patriot air defense systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-21
2022-04-05 | Contractor Technical Assistance, Patriot | 95 | Asymmetric | Support for training, fielding, operations, and sustainment of the Patriot system. This support is supposed to improve the readiness of Taiwan's Patriot systems and ensure readiness for operations. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-22
2022-06-08 | Ship Spare Parts | 120 | Traditional | Spare and repair parts for manned surface warships, from US Navy stocks and approved US Navy vendors. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-ship
2022-07-15 | Blanket Order Contractor Technical Support | 108 | Traditional | Spare and repair parts for tanks and other ground combat vehicles, small arms, and other capabilities. Classified as "Traditional" because tanks are a traditional capability, but the scope of this sale means it could include support for asymmetric systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-23
2022-09-02 | Surveillance Radar Program Support | 665.4 | Traditional | Operation and maintenance support for a missile and air defense early warning radar. Classified as "Traditional" due to the radar's immobility and vulnerability to attack. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-24
2022-12-06 | Aircraft Spare Parts, Standard | 330 | Traditional | Replenishment of standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-26
2022-12-06 | Aircraft Spare Parts, Non-Standard | 98 | Traditional | Replenishment of non-standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-25
2023-06-29 | Foreign Military Sales Order II | 108 | Asymmetric | Spare and repair parts for wheeled vehicles, small arms, and other weapons systems. Coded as "Asymmetric" because many of Taiwan's asymmetric weapons systems (e.g. ground-based anti-ship and anti-air missiles, missile defense systems, mobile command and control systems) use wheeled vehicles, but the scope of the sale means it could include support for traditional systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-28
2023-12-15 | C4 Life Cycle Support | 300 | Asymmetric | Life cycle support to maintain C4 capabilities (command, control, communications, and computers) associated with Taiwan's Syun An program. Spare and repair parts for C4 equipment. Also covers software development and maintenance of technical labs on US te | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-31
Change from Nov 23
Maintenance Total, Jan 24 | 3774 | $300 increase
Asymmetric Maintenance Total, Jan 24 | 1223 | $300 increase
Traditional Maintenance Total, Jan 24 | 2551 | No Change
| Asymmetric, Jan 24 Total | Traditional, Jan 24 Total
Trump | 620 | 1230
Biden | 603 | 1321.4

## Global Arms Sales Post-UA War
Date of Sale | Dollar Amount (Millions) | Primary Capability Sold | Secondary Capabilities Sold | Country | Region | Taiwan Backlog Overlap | Overlap Explanation | Source | Additional Sources
2022-02-03 | 23.7 | Multifunctional Information Distribution System-Low Volume Terminals (MIDS-LVT) (31) | MIDS-LVT Block 1 Upgrade (11); MIDS-LVT Block 2 Upgrade (31) | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/saudi-arabia-multifunctional-information-distribution-system-low
2022-02-03 | 4210 | F-16C/D Block 70 fighter aircraft (12 Cs, 4 Ds) | Engines (21); multiple avionics for the aircraft; multiple guided and unguided munitions, no missiles | Jordan | Middle East | Yes (Primary) | Taiwan purchased the same type of F-16s from the United States in 2019. | https://www.dsca.mil/press-media/major-arms-sales/jordan-f-16-cd-block-70-aircraft
2022-02-08 | 70 | Guided Multiple Launch Rocket System (GMLRS) Rockets (114) | Reduced Range Practice Rockets (114) | Jordan | Middle East | Yes (Primary) | Taiwan did purchase HIMARS which uses the GMLRS rocket. The original DSCA announcement only mentions ATACMS in the Taiwan sale, but other reporting indicates Taiwan modified the purchase to include GMLRS. | https://www.dsca.mil/press-media/major-arms-sales/jordan-guided-multiple-launch-rocket-systems-gmlrs-alternate-warhead
2022-02-10 | 13900 | F-15ID fighter aircraft (36) | Aircraft engines (72 installed, 15 spares); multiple avionics for the aircraft | Indonesia | Indo-Pacific | Yes (Secondary) | Some overlap in avionics, particularly the MS-110 reconnaissance pod. But overlap is relatively minor. | https://www.dsca.mil/press-media/major-arms-sales/indonesia-f-15id-aircraft
2022-02-17 | 6000 | M1A2 SEPv3 Abrams tanks (250) | Counter-IED systems (250); M88A2 Hercules Combat Recovery Vehicles (26); M1110 joint assault bridges (17); M2 .50 caliber machine guns (276); M240C 7.62mm machine guns (500); various 120mm tank ammunition rounds | Poland | Europe (NATO) | Yes (Primary) | Taiwan's Abrams tanks are built to a slightly different specification, but there is a great deal of overlap between them. | https://www.dsca.mil/press-media/major-arms-sales/poland-m1a2-sepv3-main-battle-tank
2022-02-22 | 122 | Large Aircraft Infrared Countermeasures (LAIRCM) for C-17, KC-30, and C-130 aircraft | LAIRCM System Processor Replacements (27); Guardian Laser Turret Assemblies (30); replacements and other sensors, unspecified quantity | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-laircm-line-replaceable-units-lrus
2022-03-15 | 950 | MH-60R Helicopters (8) | Helicopter engines (20); Hellfire missiles (32); various other munitions, avionics, and munition launch equipment | Spain | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/spain-mh-60r-multi-mission-helicopters-support
2022-03-17 | 700 | Ballistic Missile Defense Radar (BMDR) (1) and Command and Control Battle Management and Communications (C2BMC) nodes (2) | Combined radar-equipment shelter; encryption devices; secure communication equipment | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-ballistic-missile-defense-radar-bmdr-and-command-and
2022-03-24 | 176 | M270 Multiple Launch Rocket System (MLRS) Upgrades (9) | Various hardware related to the upgrade; 2 years of spare parts | Bahrain | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/bahrain-m270-multiple-launch-rocket-systems-mlrs-upgrade
2022-04-04 | 1673 | F-16C/D Block 70 fighter aircraft (4 Cs, 4 Ds) | Engines (11); multiple avionics for the aircraft; multiple munitions including AMRAAM, AIM-9X, and JDAM | Bulgaria | Europe (NATO) | Yes (Primary) | Taiwan purchased the same type of F-16s from the United States in 2019. Additionally, significant overlap between munitions for the Bulgarian F-16s and Taiwan's F-16s. | https://www.dsca.mil/press-media/major-arms-sales/bulgaria-f-16-cd-block-70-aircraft
2022-04-14 | 997 | AH-1Z Attack Helicopters (12) | Helicopter engines (28); weapon guidance systems; 20mm cannons | Nigeria | Africa | No |  | https://www.dsca.mil/press-media/major-arms-sales/nigeria-ah-1z-attack-helicopter-related-fms-acquisitions
2022-04-19 | 42 | Multifunctional Information Distribution System Joint Tactical Radio System (MIDS JTRS) (106) | MIDS JTRS terminals; LVT Cryptographic Modules; upgrade and retrofit kits for existing radio systems | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-defense-articles-related-multifunctional-information
2022-04-25 | 165 | Non-Standard Ammunition |  | Ukraine | Europe (Non-NATO) | No | Ammunition is for Soviet and Russian designed artillery and mortars in Ukraine's arsenal. No overlap with Taiwan ammunition. | https://www.dsca.mil/press-media/major-arms-sales/ukraine-non-standard-ammunition
2022-05-19 | 691 | TOW 2A Radio Frequency Missiles (5,000) | Missile support equipment; spare parts; training | Egypt | Middle East | Yes (Partial) | Taiwan has also purchased TOW missiles, with delivery expected in 2024. Taiwan purchased the B variant while Egypt purchased the A variant. | https://www.dsca.mil/press-media/major-arms-sales/egypt-tow-2a-radio-frequency-rf-missiles-and-support
2022-05-26 | 117 | AIM-9X missiles (72 Block II and 43 Block II+) |  | Netherlands | Europe (NATO) | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-aim-9x-block-ii-missiles
2022-05-26 | 385 | HIMARS (20) | Various types of missiles and rockets, including ATACMS (10), GMLRS (150 of various types); radio equipment; practice rockets | Australia | Indo-Pacific | Yes (Primary) | Overlap in both the HIMARS launchers and the ammunition. | https://www.dsca.mil/press-media/major-arms-sales/australia-himars-launchers
2022-05-26 | 2600 | CH-47F Chinook Helicopters (23) | Helicopter engines (56); various avionics; various communication systems | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-ch-47f-chinook-helicopters\
2022-06-21 | 94 | AGM-88E2 Missiles (15) | Various guidance systems, rocket motors, and warheads for the missiles. | Australia | Indo-Pacific | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/australia-agm-88e2-aargm-e2-missiles
2022-06-22 | 22.7 | Precision Guided Munitions (gravity bombs) | GBU-39/B Small Diameter Bombs (239); Mk-82 500 pound general purpose bombs (204); BLU-109 2,000 pound Hard Target Penetrator bombs (50) | Various | Europe (NATO) | Yes (Partial) | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/nato-support-and-procurement-agency-nspa-precision-guided-munitions
2022-07-15 | 130 | Mk 54 Lightweight Torpedoes (31) | Recoverable Exercise Torpedo; spare parts; air launch accessories for rotary wing | South Korea | Indo-Pacific | No | Taiwan purchased torpedo conversion kits in 2017, but these kits would upgrade torpedoes already in Taiwan's arsenal. | https://www.dsca.mil/press-media/major-arms-sales/korea-mk-54-lightweight-torpedoes
2022-07-15 | 500 | HIMARS (6) | Various types of rocket ammunition for the HIMARS system, 36 each of GMLRS alternative warhead, unitary high explosive, and extended range variants; ATACMS (18) | Estonia | Europe (NATO) | Yes (Primary) | Overlap in both the HIMARS launchers and the ammunition. | https://www.dsca.mil/press-media/major-arms-sales/estonia-m142-high-mobility-artillery-rocket-system-himars
2022-07-15 | 950 | AIM-120 air to air missiles (205 D, 60 C-8 or D) | AIM-120 control sections, captive air training missiles, containers; integration support and test equipment | Norway | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/norway-aim-120-c-8-or-d-advanced-medium-range-air-air-missiles
2022-07-21 | 206 | Oceanographic Observation Equipment Systems |  | UAE | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-oceanographic-observation-equipment-system
2022-07-21 | 235 | AGM-158B (JASSM-ER) air-to-ground missiles (80) | Missile containers, support equipment, spare parts | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-joint-air-surface-standoff-missiles-extended-range-jassm-er
2022-07-21 | 397 | Weapons for Eurofighter Typhoon | AIM-120 C-7/8 AMRAAM (60); Mk-83 2,000 pound bombs (250); Mk-83 1,000 pound bombs (501); JDAM Tail Kits (350); other gravity bombs | Kuwait | Middle East | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/kuwait-advanced-weapons-support-eurofighter-typhoon-aircraft-program
2022-07-21 | 1219 | Patriot GEM-T Missiles (96) | Various support equipment and training equipment. | Netherlands | Europe (NATO) | Potential | Taiwan operates Patriot systems, and US sales of maintenance support mention the GEM missile variant, but it is unclear if Taiwan is waiting on delivery of additional interceptors. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-patriot-mim-104e-guidance-enhanced-missile-tactical-gem-t
2022-07-25 | 293 | AIM-120 air to air missiles (C-7/8 variants) (150) | AMRAAM Guidance Sections (3); missile containers and control sections; spare parts | Japan | Indo-Pacific | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-120c-78-advanced-medium-range-air-air-missiles-amraams
2022-07-25 | 630 | Munitions for F-15SG fighter aircraft | Gravity bombs of various size and guidance | Singapore | Indo-Pacific | Yes (Secondary) | Taiwan did purchase some JDAM guidance kits that overlap with the guidance kits in this sale in their 2019 purchase of F-16s. The overlap is relatively small. | https://www.dsca.mil/press-media/major-arms-sales/singapore-munitions-and-follow-training-and-sustainment-peace-carvin-v
2022-07-28 | 8400 | F-35 fighter aircraft (35) | Various munitions, including AIM-120 C-8 AMRAAM (105); AIM-9X (75 Block II+); JDAM guidance kits | Germany | Europe (NATO) | Yes (Secondary) | Overlap in AMRAAM, AIM-9X, and JDAM tail kits | https://www.dsca.mil/press-media/major-arms-sales/germany-f-35-aircraft-and-munitions
2022-08-01 | 300 | Javelin Lightweight Command Launch Units (513) | Javelin Outdoor Trainers; vehicle launcher electronics; technical assistance | United Kingdom | Europe (NATO) | No | While Taiwan operates Javelin systems, the Lightweight Command Launch Unit is a recent development that reached initial low-rate production in 2022. Taiwan has not purchased the lighweight variant yet. | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-javelin-lightweight-command-launch-units
2022-08-02 | 2245 | THAAD Interceptors (96) | Launch Control Stations (2); Tactical Operations Stations (2); spare parts; support and testing equipment | UAE | Middle East | No | Taiwan does not operate the THAAD system. | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-terminal-high-altitude-area-defense-thaad-system
2022-08-02 | 3050 | Patriot GEM-T Missiles (300) | Tools and test equipment; training equipment; spare parts | Saudi Arabia | Middle East | Potential | Taiwan operates Patriot systems, and US sales of maintenance support mention the GEM missile variant, but it is unclear if Taiwan is waiting on delivery of additional interceptors. | https://www.dsca.mil/press-media/major-arms-sales/saudi-arabia-patriot-mim-104e-guidance-enhanced-missile-tactical
2022-08-09 | 74 | Javelin Missiles (222) | Javelin Command Launch Units (33); missile simulation rounds; technical assistance | Brazil | Latin America | Yes (Primary) | Taiwan is waiting on delivery of 400 Javelin missiles. Half expected to be delivered in 2023, half in 2024. | https://www.dsca.mil/press-media/major-arms-sales/brazil-javelin-missiles
2022-08-25 | 141 | Ground Command and Control Equipment | MIDS-JTRS systems (6); KY-100 Narrowband Terminalsl KIV-78 and 77 Cryptographic Appliques | Morocco | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/morocco-ground-command-and-control
2022-08-25 | 1950 | UH-60M Blackhawk Helicopters (40) | Helicopter Engines; avionics; radio equipment | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-uh-60m-black-hawk-helicopters
2022-10-06 | 3000 | NASAMS Medium Range Air Defense System (7) | AIM-120 C-8 AMRAAM (63); AMRAAM-ER (63); AIM-9X (63); various communication and electronic systems | Kuwait | Middle East | Yes (Secondary) | Taiwan has not purchased the NASAM system yet, but it is expected to purchase in 2024 due to competing demands on production, including from Ukraine. Taiwan has purchased AIM-120 C-8 and AIM-9X missiles in its 2023 purchase of F-16 munitions | https://www.dsca.mil/press-media/major-arms-sales/kuwait-national-advanced-surface-air-missile-system-nasams-medium | https://gagadget.com/en/weapons/172996-taiwan-will-buy-nasams-air-defense-systems-to-defend-against-china/
2022-10-20 | 450 | SM-6 Block 1 Missiles (32) | Mk-21 VLS canisters; handling equipment; spare parts | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-standard-missile-6-block-i-sm-6-blk-i-missiles
2022-11-02 | 535 | GMLRS Rocket Pods, various quantities and types of warhead |  | Finland | Europe (NATO) | Yes (Primary) | Taiwan has purchased GMLRS rockets as part of the 2020 HIMARS sale. | https://www.dsca.mil/press-media/major-arms-sales/finland-guided-multiple-launch-rocket-systems-gmlrs
2022-11-02 | 6350 | C-130 J-30 Transport Aircraft (24) | Aircraft engines; spare parts; avionics and radio equipment | Australia | Indo-Pacific | No | Taiwan operates C-130 aircraft but it does not have any in the backlog. | https://www.dsca.mil/press-media/major-arms-sales/australia-c-130j-30-aircraft
2022-11-08 | 380 | AMRAAMs for F-16 and F-35 aircraft (120 C-8 variant) | Spare control sections and containers, AMRAAM C-8 Guidance Sections (10) | Belgium | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/belgium-advanced-medium-range-air-air-missiles-f-16-and-f-35-programs
2022-11-09 | 385 | AGM-154C Joint Stand Off Weapons (48) | Various test items, spares, and repair equipment. | Oman | Middle East | Yes (Primary) | Taiwan purchased AGM-154Cs in 2017. Delivery was expected in 2023, but no confirmation that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/oman-joint-stand-weapons-jsow
2022-11-09 | 495 | HIMARS (8) | GMLRS Missile Pods of various warhead types (36 apiece, 4 types); ATACMS missile pods (18) | Lithuania | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/lithuania-m142-high-mobility-artillery-rocket-system-himars
2022-11-15 | 700 | PAC-3 MSE missiles (72) | Telemetry kits; PAC-3 MSE trainers; launch stations items | Switzerland | Europe (Non-NATO) | Yes (Primary) | According to US reporting, the US modified a 2010 sale of Patriot systems to Taiwan in 2022 to include 100 MSE missiles for $882 million. | https://www.dsca.mil/press-media/major-arms-sales/switzerland-patriot-advanced-capability-pac-3-missile-segment-enhanced | https://www.bloomberg.com/news/articles/2022-12-05/us-upgrades-taiwan-weapons-package-with-newer-patriot-missiles?srnd=asia-politics&leadSource=uverify%20wall#xj4y7vzkg
2022-11-28 | 323 | AIM-9X missiles (40 Block II) and AGM-154 Joint Stand Off Weapons (48) |  | Finland | Europe (NATO) | Yes (Primary) | Taiwan purchsed AGM-154Cs in 2017 and AIM-9Xs in 2022 | https://www.dsca.mil/press-media/major-arms-sales/finland-aim-9x-block-ii-tactical-missiles-and-agm-154-joint-standoff
2022-11-29 | 1000 | Fixed Site-Low, Slow, Small Unmanned Aircraft System Integrated Defeat System (FS-LIDS) (10) | Coyote Block 2 interceptors (200); Counter Unmanned Electronic Warfare Systems; radio systems | Qatar | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/qatar-fixed-site-low-slow-small-unmanned-aircraft-system-integrated
2022-12-01 | 380 | FIM-92K Stinger MANPADS (350) | Production Verification Flight Test (PVFT) missiles (5) | Finland | Europe (NATO) | No | Taiwan purchased 250 FIM-92F Stingers in 2019. Press reports from 2023 indicated that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/finland-stinger-man-portable-ground-air-missiles | https://www.thedefensepost.com/2023/05/30/taiwan-stinger-missiles-us/
2022-12-06 | 1500 | CH-47F Chinook Helicopters (18) | Helicopter engines, avionics, and communication systems | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/korea-ch-47f-chinook-helicopters\
2022-12-06 | 3750 | M1A1 Abrams Tanks (116) | Hercules Combat Recovery Vehicles (12); Joint Assault Bridges (8); M577A3 Command Vehicles (6); Humvees (26); tank ammunition | Poland | Europe (NATO) | Yes (Primary) | The Abrams variant is unspecified but there is otherwise considerable overlap between the Poland sale and Taiwan's 2019 Abrams purchase. | https://www.dsca.mil/press-media/major-arms-sales/poland-m1a1-abrams-main-battle-tanks
2023-02-07 | 10000 | HIMARS (18) | HIMARS Launcher Loader Module kits (468); ATACMS (45); various GMLRS warhead configuration rockets all in the 400s or 500s quantity | Poland | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/poland-high-mobility-artillery-rocket-system-himars-0
2023-02-09 | 55 | Air to Ground Munitions Kits and Equipment |  | Singapore | Indo-Pacific | Yes (Secondary) | Minor overlap in munitions mentioned in 2019 F-16 sale to Taiwan. | https://www.dsca.mil/press-media/major-arms-sales/singapore-air-ground-munitions-kits-and-services
2023-02-14 | 250 | Medical Information System |  | Kuwait | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kuwait-medical-information-system-kuwait-military-medical-command-kmmc
2023-02-16 | 670 | HIMARS (20) | ATACMS (80); various GMLRS warhead configuration rockets 30s quantity; unspecified number of support vehicles | Netherlands | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-m142-high-mobility-artillery-rocket-system-himars
2023-02-27 | 506 | Advanced Anti-Radiation Guided Missiles-Extended Range (63, AGM-88G variant) | Captive Air Training Missiles (20); AGM-88G Dummy Air Training Missiles | Australia | Indo-Pacific | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/australia-advanced-anti-radiation-guided-missiles-extended-range-aargm
2023-02-28 | 125 | Javelin Missiles (600, FGM-148F variant) |  | United Kingdom | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of 400 Javelin missiles. Half expected to be delivered in 2023, half in 2024. | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-javelin-missiles
2023-03-07 | 60 | Javelin Missiles (255, FGM-148F variant) |  | Australia | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of 400 Javelin missiles. Half expected to be delivered in 2023, half in 2024. | https://www.dsca.mil/press-media/major-arms-sales/australia-javelin-fgm-148f-missiles
2023-03-07 | 1381 | E-2D Advanced Hawkeye Airborne Early Warning aircraft (5) | Aircraft engines (12); APY-9 Radars (5); avionics, radio, and electronic systems | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-e-2d-advanced-hawkeye-ahe-airborne-early-warning-and-control
2023-03-14 | 104 | Heavy Gun Carriers Joint Light Tactical Vehicles (95) |  | Romania | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/romania-m1278a1-heavy-gun-carriers-joint-light-tactical-vehicles-jltvs
2023-03-16 | 150 | Hellfire Missiles (800 AGM-114R2 variant) | Hellfire Captive Air Training Missiles (4); support and technical assistance | Poland | Europe (NATO) | No | Taiwan possesses Hellfire missiles, but does not currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/poland-hellfire-missiles
2023-03-16 | 895 | Tomahawk All Up Rounds (200 Block V, 20 Block IV) | Tactical Tomahawk Weapon Control System; Theater Mission Planning Center; various support equipment of unspecified quantity | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-tomahawk-weapon-system
2023-03-17 | 268 | Assault Amphibious Vehicles (63) | AAV command variant (9); AAV recovery variant (4); grenade launchers, thermal sight systems | Greece | Europe (NATO) | No | Taiwan possesses AAVs but it does not have currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/greece-assault-amphibious-vehicles-aavs
2023-03-29 | 350 | AH-1W Multi-Role Helicopter refurbishment (24) |  | Bahrain | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/bahrain-ah-1w-helicopter-refurbishment
2023-04-11 | 250 | AGM-154C Joint Stand Off Weapons (40) | Training missiles, containers, mission planning, integration support | Morocco | Middle East | Yes (Primary) | Taiwan purchased AGM-154Cs in 2017. Delivery was expected in 2023, but no confirmation that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/morocco-joint-stand-weapons-jsow
2023-04-11 | 524 | HIMARS (18) | ATACMs (40); GMLRS rockets with various ammunition (36 each of 2 variants); Humvees (9); practice rocket pods (40); various radio and vehicle equipment | Morocco | Middle East | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/morocco-high-mobility-artillery-rocket-systems-himars
2023-04-17 | 259 | F-16 Avionics Upgrade |  | Turkey | Europe (NATO) | No | Taiwan operates F-16 aircraft and purchased 66 C/D Block 70 in 2019 that have not been delivered. However, that sale does not indicate an overlap in avionics sold to Turkey. | https://www.dsca.mil/press-media/major-arms-sales/turkiye-f-16-avionics-upgrade
2023-04-28 | 31 | Advanced Precision Kill Weapon System-II (768) | Unspecified quantity of spares, support equipment, etc. | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-advanced-precision-kill-weapon-system-ii
2023-05-02 | 110 | Naval Strike Missile Coastal Defense System (1) | Unspecified quantity of training missiles, containers, mobile operational platforms | Latvia | Europe (NATO) | No | Taiwan does not operate the Naval Strike Missile system. But it would be a welcome asymmetric capability. | https://www.dsca.mil/press-media/major-arms-sales/latvia-naval-strike-missile-coastal-defense-system
2023-05-03 | 650 | Refurbishment and Modernization of AH-1Z (6) and UH-1Y (2) helicopters | Helicopter Engines (22); GPS navigation systems (14); radios (24) | Czech Republic | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/czech-republic-ah-1z-and-uh-1y-refurbishmentmodernization
2023-05-04 | 207 | Surveillance Towed Array Sensor System Expeditionary (SURTASS-E) (unspecified quantity) |  | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-surveillance-towed-array-sensor-system-expeditionary-surtass
2023-05-09 | 124 | AN/AAQ-33 Sniper Targeting Pods (34) |  | Poland | Europe (NATO) | Yes (Primary) | Taiwan has purchased Sniper targeting pods for F-16 aircraft, and in 2023 purchased an unspecified infrared track and targeting system that might be a Sniper though is unspecified | https://www.dsca.mil/press-media/major-arms-sales/poland-sniper-advanced-targeting-pods
2023-05-09 | 250 | Heavy Gun Carriers Joint Light Tactical Vehicles (192) | Unspecified quantites of various small arms, spare parts, other equipment | Slovakia | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/slovakia-m1278a1a2-heavy-gun-carriers-joint-light-tactical-vehicles
2023-05-11 | 8500 | CH-47F Helicopters (60) | Helicopter Engines (140); various helicopter avionics and communication equipment | Germany | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/germany-ch-47f-chinook-helicopters
2023-05-24 | 285 | NASAMS Medium Range Air Defense System (1) | Fire Distribution Center; canister launchers; other equipment | Ukraine | Europe (Non-NATO) | No | Taiwan has not purchased the NASAM system yet, but it is expected to purchase in 2024 due to competing demands on production, including from Ukraine. | https://www.dsca.mil/press-media/major-arms-sales/ukraine-national-advanced-surface-air-missile-system-nasams
2023-06-02 | 110 | Mk 41 VLS Launchers (8) |  | Netherlands | Europe (NATO) | No | Taiwan has purchased Mk 41 VLS systems from the US in the past but does not have any on order currently. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-mk-41-vertical-launching-system-vls
2023-06-14 | 48 | Excalibur Guided 155mm Artillery Shells (271) |  | Spain | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/spain-excalibur-projectiles
2023-06-16 | 611 | MQ-9A Block 5 Unmanned Aircraft (4) | Mobile Ground Control Systems (3); Embedded GPS Systems (30); AN/APY-8 Synthetic Aperture Radars (20) | Netherlands | Europe (NATO) | Yes (Partial) | Taiwan is waiting on delivery of 4 MQ-9B drones and associated support equipment. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-mq-9a-block-5-aircraft
2023-06-27 | 5900 | P-8A Maritime Patrol Aircraft (16) | MIDS JTRS (26); GPS systems (38); LAIRCM system (25) various avionics and sensors | Canada | North America (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/canada-p-8a-aircraft
2023-06-28 | 293 | GBU-53/B Small Diameter Bomb Increment II (580) |  | Norway | Europe (NATO) | Yes (Partial) | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/norway-small-diameter-bomb-ii
2023-06-28 | 4000 | Integrated Air and Missile Defense (IAMD) Battle Command System (IBCS) | Patriot M903 Launch Stations (48); PAC-3 MSE interceptors (644); Lower Tier Air and Missile Defense Sensors (LTAMDS) (12) | Poland | Europe (NATO) | Yes (Secondary) | According to US reporting, the US modified a 2010 sale of Patriot systems to Taiwan in 2022 to include 100 MSE missiles for $882 million. | https://www.dsca.mil/press-media/major-arms-sales/poland-integrated-air-and-missile-defense-iamd-battle-command-system-0
2023-06-29 | 5620 | F-35 Fighter Aircraft and Munitions (24) | Munitions include AIM-120 C-8 (70); Small Diameter Bombs Increment II (86); AIM-9X (50) | Czech Republic | Europe (NATO) | Yes (Secondary) | Overlap in AIM-120 C-8 missiles, Small Diameter Bombs, and AIM-9X | https://www.dsca.mil/press-media/major-arms-sales/czech-republic-f-35-aircraft-and-munitions
2023-06-30 | 105 | F-16 Modernization (32) |  | Romania | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/romania-modernization-tpt-f-16s
2023-07-07 | 203 | Hellfre Missiles (1,515) |  | France | Europe (NATO) | No | Taiwan possesses Hellfire missiles, but does not currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/france-hellfire-missiles
2023-07-07 | 605 | AIM-120 C-8 AMRAAM Missiles (250) | AMRAAM Guidance Sections (6); containers; test sets and telemetry kits | Sweden | Europe (Non-NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/sweden-aim-120c-8-advanced-medium-range-air-air-missile-amraam
2023-07-19 | 2900 | AIM-120 C-8 AMRAAM Missiles (969) | AMRAAM Guidance Sections (12); Captive Air Training Missiles; KGV-135A Communications Security devices | Germany | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://dsca.mil/press-media/major-arms-sales/germany-aim-120c-8-advanced-medium-range-air-air-missiles-amraam
2023-07-31 | 120 | Assault Amphibious Vehicles (16) | AAV command variant (3); AAV recovery variant (2); various machine guns | Romania | Europe (NATO) | No | Taiwan possesses AAVs but it does not have currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/romania-assault-amphibious-vehicles
2023-08-01 | 395 | M270 Multiple Launch Rocket System (MLRS) Upgrades (unspecified amount) |  | Finland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/finland-m270a2-multiple-launch-rocket-system-mlrs-upgrade
2023-08-18 | 975 | HIMARS (22) | GMLRS Missile Pods of various warhead types (190 total); support vehicles | Australia | Indo-Pacific | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/australia-m142-high-mobility-artillery-rocket-systems-himars
2023-08-21 | 12000 | AH-64E Apache Helicopters (96) | Helicopter Engines (210); various avionics and radar; munitions including Hellfire, JAGM, Stinger | Poland | Europe (NATO) | No | Taiwan operates the AH-64E, but it does not have any on order. | https://www.dsca.mil/press-media/major-arms-sales/poland-ah-64e-apache-helicopters
2023-08-28 | 104 | JASSM-ER Missiles (50) | JASSM Anti-jam GPS; training missiles; spare parts | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-joint-air-surface-standoff-missiles-extended-range-jassm-er
2023-09-01 | 1500 | Stryker Vehicles (183) | Modular Catastrophic Recovery Systems (5); M984A4 Wrecker HEMTT (5) various electronic and sensor components | Bulgaria | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/bulgaria-stryker-vehicles
2023-09-13 | 5060 | F-35 fighter aircraft (25) | Various avionics and support equipment | South Korea | Indo-Pacific | No | This package does not include munitions for the F-35s, which is the common area of overlap with Taiwan's backlog | https://www.dsca.mil/press-media/major-arms-sales/korea-f-35-aircraft
2023-09-15 | 313 | Munitions and Sensors for MQ-9B |  | Canada | North America (NATO) | Yes (Secondary) | Taiwan purchased 4 MQ-9B aircraft in November 2020. Munitions were not included in that sale, but there is overlap in some of the sensor and communication equipment | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-18
2023-10-03 | 70 | TOW 2B Radio Frequency Missiles (301) |  | Oman | Middle East | Yes (Primary) | Taiwan has purchased 460 TOW 2B missiles with delivery expected in 2024 | https://www.dsca.mil/press-media/major-arms-sales/oman-tow-2b-radio-frequency-missiles-bgm-71f-7-rf-and-support
2023-10-04 | 2800 | Patriot Configuration 3+ Modernized Fire Units (4) | PAC-3 MSE missiles (51); Patriot M903 launch stations (24); AN/MPQ-65 radar sets (4) | Spain | Europe (NATO) | Yes (Secondary) | According to US reporting, the US modified a 2010 sale of Patriot systems to Taiwan in 2022 to include 100 MSE missiles for $882 million. | https://dsca.mil/press-media/major-arms-sales/spain-patriot-configuration-3-modernized-fire-units
2023-10-23 | 100 | AIM-120 C-8 AMRAAM Missiles (36) | Various support equipment and training equipment. | Lithuania | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/lithuania-aim-120c-8-advanced-medium-range-air-air-missiles-amraam
2023-10-23 | 500 | Anti-Radiation Guided Missiles-Extended Range AGM-88G (150) |  | Finland | Europe (NATO) | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/finland-advanced-anti-radiation-guided-missiles-extended-range-aargm
2023-10-23 | 957 | Joint Air-to-Ground Missiles (JAGM) (3,000) | Dummy missiles; technical assistance; training support | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-joint-air-ground-missiles-jagm
2023-10-24 | 74 | Rolling Airframe Missile Block 2B (63) |  | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-rolling-airframe-missiles-ram-block-2b-tactical-missiles
2023-10-24 | 220 | HIMARS (6) | GMLRS rocket pods of various warhead types (24, 2 variants); ATACMS (10) | Latvia | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/latvia-m142-high-mobility-artillery-rocket-systems
2023-11-09 | 2530 | M1A2 SEPv3 Abrams tanks (54) | M88A2 Hercules Combat Recovery Vehicles (4); Joint Assault Bridges (4); Heavy Assault Scissor Bridges (4); lots of tank ammunition | Romania | Europe (NATO) | Yes (Primary) | Taiwan's Abrams tanks are built to a slightly different specification, but there is a great deal of overlap between them. | https://www.dsca.mil/press-media/major-arms-sales/romania-m1a2-abrams-main-battle-tanks
2023-11-14 | 650 | SM-6 Block 1 Missiles (38) | Mk-21 VLS canisters; handling equipment; spare parts | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/korea-standard-missile-6-block-i-sm-6-blk-i
2023-11-15 | 52 | AIM-9X Missiles (42) | Captive Air Training Missiles (5); AIM-9X Guidance Units (5) | South Korea | Indo-Pacific | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/korea-aim-9x-block-ii-and-block-ii-plus-sidewinder-missiles
2023-11-17 | 2350 | Tomahawk All Up Rounds (200 Block IV; 200 Block V) | Tactical Tomahawk Weapon Control System (14) and other components | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-tomahawk-weapon-system
2023-12-01 | 271 | F-35 Munitions (various quantities) | AIM-120C-8 (39); JDAM Guidance Kits; gravity bombs (various); GBU-53 SDB-I (118) | South Korea | Indo-Pacific | Yes (Primary) | AIM-120C-8 overlap, some JDAM tail kit overlap | https://www.dsca.mil/press-media/major-arms-sales/korea-f-35-munitions
2023-12-04 | 85 | AN/TPQ-50 Radar (18, man portable versions) | Various support equipment and training equipment. | UAE | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-antpq-50-radar
2023-12-04 | 582 | RE-3A Tactical Airborne Surveillance System Modernization | Various electronic communication and guidance systems. | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/saudi-arabia-re-3a-tactical-airborne-surveillance-system-aircraft
2023-12-07 | 300 | MK 54 Lightweight Torpedoes (80) | Various spare parts and support equipment | Germany | Europe (NATO) | No | Taiwan purchased lightweight torpedo conversion kits, not all up rounds. | https://www.dsca.mil/press-media/major-arms-sales/germany-mk-54-lightweight-torpedoes
2023-12-09 | 106 | M830A1 120mm Tank Cartridges (13,981) |  | Israel | Middle East | Yes (Potential) | Taiwan purcahsed 120mm tank rounds as part of the big Abrams sale. | https://www.dsca.mil/press-media/major-arms-sales/israel-m830a1-120mm-tank-cartridges
2023-12-12 | 80 | Javelin Missiles (263) |  | Romania | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of 400 Javelin missiles. Half expected to be delivered in 2023, half in 2024. | https://www.dsca.mil/press-media/major-arms-sales/romania-javelin-missiles
2023-12-13 | 255 | Communications Equipment | Various quantities and types of radios and other electronic equipment | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-communications-equipment
2023-12-15 | 59 | AIM-9X Block II Missiles (44) |  | Japan | Indo-Pacific | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-9x-block-ii-sidewinder-missiles
2023-12-15 | 224 | AIM-120C-8 AMRAAM Missiles (120) |  | Japan | Indo-Pacific | Yes (Primary) | Taiwan has also purchased AIM-120C-8 missiles for its F-16 fleet. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-120c-8-advanced-medium-range-air-air-missiles-amraam
2023-12-15 | 400 | HIMARS (21) | Communication and support equipment, but no mention of HIMARS ammunition quantities in the sale. | Italy | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. | https://www.dsca.mil/press-media/major-arms-sales/italy-m142-high-mobility-artillery-rocket-systems-himars
2023-12-15 | 1950 | UH-60M Blackhawk Helicopters (35) | Various spare parts and support equipment | Greece | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/greece-uh-60m-black-hawk-helicopters
2023-12-22 | 780 | FIM-92K Stinger MANPADS (940) |  | Various | Europe (NATO) | No | Taiwan purchased 250 FIM-92F Stingers in 2019. Press reports from 2023 indicated that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/nato-support-and-procurement-agency-nspa-stinger-missiles
2023-12-29 | 147 | 155mm Artillery Shells |  | Israel | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/israel-155mm-artillery-ammunition
2024-01-10 | 129 | 28-Meter Patrol Craft Kits |  | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-28-meter-patrol-craft-kits
2024-01-10 | 200 | Light Tactical Vehicle Chassis and Fleet Build |  | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-light-tactical-vehicle-chassis-and-fleet-build
2024-01-10 | 250 | Tomahawk Weapons System Support Services |  | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-general-tomahawk-weapons-system-support-services-uplift
2024-01-11 | 75 | Javelin Missiles (246) | Lightweight Javelin Command Launch Units (6) | Kosovo | Europe (Non-NATO) | Yes (Primary) | Taiwan is waiting on delivery of 400 Javelin missiles. Half expected to be delivered in 2023, half in 2024. | https://www.dsca.mil/press-media/major-arms-sales/kosovo-javelin-missiles
2024-01-26 | 500 | Black Hawk Helicopters (8) | Helicopter engines, avionics, and communication systems | Croatia | Europe (NATO) | No | Taiwan operates the same variant of Black Hawk helicopters, but it is not waiting on any orders. | https://www.dsca.mil/press-media/major-arms-sales/croatia-uh-60m-black-hawk-helicopters-0
2024-01-26 | 8600 | F-35 Aircraft (40) | Aircraft engines, avionics, radar, no ammunition | Greece | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/greece-f-35-joint-strike-fighter-conventional-take-and-landing-ctol
2024-01-26 | 23000 | F-16 aircraft (40 new build, 79 modifications to existing airframes) | Aircraft engines, avionics, radar, lots of munitions | Turkey | Europe (NATO) | Yes (Primary) | Taiwan waiting on delivery of the same F-16 model (C/D Block 70), which is scheduled to complete in 2026. | https://www.dsca.mil/press-media/major-arms-sales/turkiye-f-16-aircraft-acquisition-and-modernization
2024-02-01 | 3990 | MQ-9B Sky Guardian UAVs (31) | Sensors, guidance and navigation systems, Hellfire missiles (170) | India | Indo-Pacific | Yes (Partial) | Taiwan has 4 MQ-9Bs in the backlog. However, Taiwan has ordered the maritime surveillance variant while India has ordered the air surveillance variant | https://www.dsca.mil/press-media/major-arms-sales/india-mq-9b-remotely-piloted-aircraft
2024-02-02 | 150 | AGM-114R2 Hellfire Missiles (386) | Various technical documents and support equipment | Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/netherlands-hellfire-missiles
2024-02-05 | 908 | JASSM-ER Missiles (120) | Separation test vehicles (2), instrument test vehicle (1), encryption devices | Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/netherlands-joint-air-surface-standoff-missiles-extended-range
2024-02-07 | 1200 | Airspace and Surface Radar Aerostat Systems | Airborne Early Warning radars with IFF capability; mooring systems; fiber optics | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-aerostat-systems
2024-02-15 | 69 | AIM-120C-8 AMRAAM Missiles (12) |  | Italy | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/italy-aim-120c-8-advanced-medium-range-air-air-missiles | This sale announcement amends/updates an earlier sale of AIM-120s to Italy that fell beneath the reporting requirement thresholds.The new sale value is above the thresholds
2024-02-15 | 150 | Small Diameter Bomb II (125) |  | Italy | Europe (NATO) | Yes (Partial) | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/italy-small-diameter-bomb-ii
2024-02-27 | 281 | HF, VHF, and UHF Radios |  | Germany | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/germany-high-frequency-very-high-frequency-and-ultra-high-frequency
2024-03-07 | 170 | BQM-177A Subsonic Sea-Skimming Aerial Targets (5) | GQM-163 target drones, classified technical publications, personnel training | South Korea | Ino | No | For the ROKN's KDX-III Batch II Aegis destroyers | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-subsonic-sea-skimming-aerial-targets-kdx-iii-batch-ii
2024-03-07 | 138 | Telecommunications services for SATCOM access to Canadian armed forces |  | Canada | North America (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/canada-mobile-user-objective-system-access
2024-03-08 | 350 | T-700 GE 401C or 401D Engines for MH-60R Helicopters (6) | Spare engine containers, repair parts, ferry support, publications | South Korea | Indo-Pacific | No | Taiwan operates Blackhawk Helicopters of a different variant. No engines currently for these helicopters in the backlog as of March 2024 | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-engines-and-sustainment-mh-60r-multi-mission
2024-03-08 | 111 | Joint Light Tactical Vehicle Heavy Gun Carriers (18) and General Purpose (7) |  | North Macedonia | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/north-macedonia-joint-light-tactical-vehicles
2024-03-12 | 219 | AIM-9X Block II Missiles (232) | AIM-9X Missile Guidance Units (16), containers, spare parts, active optical detectors | Poland | Europe (NATO) | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/poland-aim-9x-block-ii-sidewinder-missiles
2024-03-12 | 1690 | AIM-120C-8 AMRAAM (745) | AMRAAM Guidance Sections (16), LAU-129 Guided Missile Launchers (50), other spares | Poland | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/poland-aim-120c-8-advanced-medium-range-air-air-missiles
2024-03-12 | 1770 | AGM-158B-2 JASSM-ER Missiles (821) | Test equipment, weapon support and integration. | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-agm-158b-2-joint-air-surface-standoff-missile-extended-range
2024-03-15 | 91 | AIM-9X Block II+ Missiles (28) | Tactical Guidance Units (4), Captive Training Missiles (8), etc. | Italy | Europe (NATO) | Yes (Partial) | Taiwan purchased AIM-9X missiles in September 2022. These missiles were just Block II and not II+. Unclear what the difference is. | https://www.dsca.mil/press-media/major-arms-sales/italy-aim-9x-sidewinder-missiles
2024-03-19 | 2200 | M1A2 SEPv3 Abrams Tanks (50) | Hercules Combat Recovery Vehicles (4); Joint Assault Bridgets (8); Assault Breacher Vehicles (8); Ammunition | Bahrain | Middle East | Yes (Primary) | Taiwan purchased Abrams tanks in 2019 that are scheduled for delivery from 2024-2026. Taiwan has a slightly different Abrams variant, but it is mostly the same. | https://www.dsca.mil/press-media/major-arms-sales/bahrain-m1a2-abrams-main-battle-tanks
2024-03-19 | 260 | Javelin FGM-148F Missiles (612) | Javelin Lightweight Command Launch Units (200) | Morocco | Middle East | Yes (Primary) | Taiwan is waiting on delivery of Javelin missiles, expected to be delivered in 2023 and 2024. | https://www.dsca.mil/press-media/major-arms-sales/morocco-javelin-missiles
2024-04-09 | 138 | HAWK Phase III Missile System Sustainment |  | Ukraine | Europe (Non-NATO) | No | Tiawan retired its HAWK air defense systems in 2023 | https://www.dsca.mil/press-media/major-arms-sales/ukraine-hawk-phase-iii-missile-system-sustainment
2024-04-10 | 101 | Multifunctional Information Distribution Systems (50) | MIDS-LVT Block Upgrade 2 Retrofit Kits (100) | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-multifunctional-information-distribution-systems
2024-04-15 | 140 | C-172 and AC/RC-208 Aircraft Logistics Support |  | Iraq | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/iraq-c-172-and-acrc-208-aircraft-contractor-logistics-support
2024-04-18 | 143 | BT-67 Aircraft (unknown quantity) |  | Argentina | Latin America | No |  | https://www.dsca.mil/press-media/major-arms-sales/argentina-basler-bt-67-aircraft
2024-04-24 | 1275 | AARGM-ER Missiles (360) | AGM-88GAARGM-ER Guidance Sections (8 spares); AGM-88G AARGM-ER Control Sections (8 spares); various spare and repair parts | Poland | Europe (NATO) | No | Taiwan has AGM-88s in the backlog, but not the AARGM-ER model. | https://www.dsca.mil/press-media/major-arms-sales/poland-advanced-anti-radiation-guided-missiles-extended-range
2024-04-24 | 700 | AARGM-ER Missiles (265) | AGM-88GAARGM-ER Guidance Sections (8 spares); AGM-88G AARGM-ER Control Sections (8 spares); various spare and repair parts | Netherlands | Europe (NATO) | No | Taiwan has AGM-88s in the backlog, but not the AARGM-ER model. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-advanced-anti-radiation-guided-missiles-extended-range

## Ukraine PDA Overlap
Date of Transfer | Transfer Authority | Backlogged Capability Transferred | Number of Capability Overlap, Rolling Total | Overlapped Capabilities, Rolling Total | Note | Source
2022-03-16 | Presidential Drawdown | Javelin (2,000) | 1 | Javelin (2,000) | Taiwan is waiting on delivery of 400 Javelins. Received first half in 2023, delivery expected to complete in 2024. | https://www.defense.gov/News/Releases/Release/Article/2968561/statement-by-secretary-of-defense-lloyd-j-austin-iii-on-security-assistance-for/
2022-04-07 | Presidential Drawdown | Javelin (unspecified) | 1 | Javelin (2,000+) | Taiwan is waiting on delivery of 400 Javelins. Received first half in 2023, delivery expected to complete in 2024. | https://www.defense.gov/News/Releases/Release/Article/2992414/fact-sheet-us-security-assistance-to-ukraine/
2022-04-13 | Presidential Drawdown | Javelin (500) | 1 | Javelin (2,500+) | Taiwan is waiting on delivery of 400 Javelins. Received first half in 2023, delivery expected to complete in 2024. | https://www.defense.gov/News/Releases/Release/Article/2999113/800-million-in-additional-security-assistance-for-ukraine/
2022-05-06 | Presidential Drawdown | Javelin (5,500+) | 1 | Javelin (8,000+) | Taiwan is waiting on delivery of 400 Javelins. Received first half in 2023, delivery expected to complete in 2024. | https://www.defense.gov/News/Releases/Release/Article/3027295/fact-sheet-on-us-security-assistance-for-ukraine/
2022-06-01 | Presidential Drawdown | HIMARS and Ammunition; Javelins (1,000) | 3 | Javelin (9,000+); HIMARS; HIMARS ammunition | Added HIMARS ammunition and launchers. | https://www.defense.gov/News/Releases/Release/Article/3049472/700-million-in-additional-security-assistance-for-ukraine/
2022-06-15 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 3 | Javelin (9,000+); HIMARS; HIMARS ammunition |  | https://www.defense.gov/News/Releases/Release/Article/3064351/1-billion-in-additional-security-assistance-for-ukraine/
2022-06-15 | Ukraine Security Assistance Initiative | Harpoon Coastal Defense Systems (2) | 4 | Javelin (9,000+); HIMARS; HIMARS amunition; Harpoon* (2) | Taiwan is waiting on delivery of 100 Harpoon coastal defense system launchers and 400 missiles. | https://www.defense.gov/News/Releases/Release/Article/3064351/1-billion-in-additional-security-assistance-for-ukraine/
2022-07-01 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 4 | Javelin (9,000+); HIMARS; HIMARS amunition; Harpoon* (2) |  | https://www.defense.gov/News/Releases/Release/Article/3081993/820-million-in-additional-security-assistance-for-ukraine/
2022-07-01 | Ukraine Security Assistance Initiative | NASAMS (2) | 5 | Javelin (9,000+); HIMARS; HIMARS amunition; Harpoon* (2); NASAMS* (2) | Taiwan is waiting on delivery of AIM-120 and AIM-9X missiles, which are used by NASAMS. Taiwan has not yet purchased NASAMS batteries, but press reports indicate that it has included money in its 2024 defense budget to purchase 4 NASAMS. | https://www.defense.gov/News/Releases/Release/Article/3081993/820-million-in-additional-security-assistance-for-ukraine/
2022-07-08 | Presidential Drawdown | HIMARS (4); HIMARS Ammunition (unspecified) | 5 | Javelin (9,000+); HIMARS (12); HIMARS amunition; Harpoon* (2); NASAMS* (2) | A fact sheet from June 24, 2022 indicated the US has previously transferred 8 HIMARS to Ukraine. The four in this drawdown brings the total number transferred to 12. | https://www.defense.gov/News/Releases/Release/Article/3087750/400-million-in-additional-security-assistance-for-ukraine/
2022-07-22 | Presidential Drawdown | HIMARS (4); HIMARS Ammunition (unspecified) | 5 | Javelin (9,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (2) |  | https://www.defense.gov/News/Releases/Release/Article/3102984/270-million-in-additional-security-assistance-for-ukraine/
2022-08-01 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 5 | Javelin (9,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (2) |  | https://defense.gov/News/Releases/Release/Article/3112377/550-million-in-additional-security-assistance-for-ukraine/
2022-08-08 | Presidential Drawdown | HIMARS Ammunition (unspecified); NASAMS Ammunition; Javelin (1,000) | 5 | Javelin (10,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (2) | Munitions for NASAMS are unspecified in the announcement. However, the system uses the AIM-120, AIM-9X missiles, which Taiwan is waiting on delivery of. | https://www.defense.gov/News/Releases/Release/Article/3120059/1-billion-in-additional-security-assistance-for-ukraine/
2022-08-19 | Presidential Drawdown | HIMARS Ammunition (unspecified); HARMS Ammunition (Unspecified); TOW Missiles (1,500); Javelin (1,000) | 7 | Javelin (11,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (2); HARM Missiles; TOW Missiles (1,500) | This announcement adds HARM and TOW to the overlap. Taiwan's order of TOW missiles should be complete in 2024. Taiwan recently cleared a HARM backlog, but HARMs were part of a F-16 munitions sale in 2023 that has not been delivered yet. | https://www.defense.gov/News/Releases/Release/Article/3134457/775-million-in-additional-security-assistance-for-ukraine/
2022-08-24 | Ukraine Security Assistance Initiative | NASMS (6) and Munitions | 7 | Javelin (11,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) | More NASAMS via USAI authority. Taiwan has indicated that it will purchase NASMS via the FMS process in 2024, but it has not made an order yet. | https://www.defense.gov/News/Releases/Release/Article/3138105/nearly-3-billion-in-additional-security-assistance-for-ukraine/
2022-09-08 | Presidential Drawdown | HIMARS Ammunition (unspecified); HARM Missiles (unspecified) | 7 | Javelin (11,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3152071/675-million-in-additional-security-assistance-for-ukraine/
2022-09-15 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 7 | Javelin (11,000+); HIMARS (16); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3160503/600-million-in-additional-security-assistance-for-ukraine/
2022-09-28 | Ukraine Security Assistance Initiative | HIMARS (18) and Ammunition | 7 | Javelin (11,000+); HIMARS* (16 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) | First time of HIMARS launchers mentioned as part of a USAI package. Since these capabilities are not produced yet, they will compete with Taiwan's HIMARS purchase for production line space, as well as HIMARS orders from other FMS sales. | https://www.defense.gov/News/Releases/Release/Article/3173378/11-billion-in-additional-security-assistance-for-ukraine//
2022-10-04 | Presidential Drawdown | HIMARS (4); HIMARS Ammunition (unspecified) | 7 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3179323/625-million-in-additional-security-assistance-for-ukraine/
2022-10-14 | Presidential Drawdown | HIMARS Ammunition (unspecified); HARM Missiles | 7 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3189571/725-million-in-additional-security-assistance-for-ukraine/
2022-10-28 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 7 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3203509/275-million-in-additional-presidential-drawdown-security-assistance-for-ukraine/
2022-11-10 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 7 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) | This drawdown also included HAWK missiles. Taiwan used to operate the HAWK system, but it recently retired the system. | https://www.defense.gov/News/Releases/Release/Article/3216287/400-million-in-additional-assistance-for-ukraine/
2022-11-23 | Presidential Drawdown | NASAMS Munitions (unspecified); HIMARS Ammunition (unspecified); HARM Missiles (unpsecified) | 7 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3227217/400-million-in-additional-assistance-for-ukraine/
2022-12-09 | Presidential Drawdown | HIMARS Ammunition (unspecified) | 7 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500) |  | https://www.defense.gov/News/Releases/Release/Article/3241679/275-million-in-additional-assistance-for-ukraine/
2022-12-21 | Presidential Drawdown | Patriot Munitions (unspecified); HIMARS Ammunition (unspecified); HARM Missiles (Unspecified) | 8 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (1,500); Patriot Munitions | This drawdown adds Patriot munitions to the overlap. Seperate reporting indicated that the US transferred to Ukraine the same type of Patriot interceptor that was in a December 2022 modification to an older Patriot sale to Taiwan. Taiwan is not waiting on any Patriot launchers, only interceptors. | https://www.defense.gov/News/Releases/Release/Article/3252782/185-billion-in-additional-security-assistance-for-ukraine/
2023-01-06 | Presidential Drawdown | TOW Missiles (500); HIMARS Ammunition (unspecified); Paladin Howitzers (18) | 9 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,000); Patriot Munitions; Paladin Howitzers (18) | This drawdown adds Paladin self-propelled howitzers to the overlap. Taiwan did place an FMS order for Paladins in August 2021. However, there is conflicting information about the current status of that sale, with some reports saying the sale was cancelled while others saying it has only been delayed. | https://www.defense.gov/News/Releases/Release/Article/3261263/more-than-3-billion-in-additional-security-assistance-for-ukraine/
2023-01-19 | Presidential Drawdown | NASAMS Munitions (Unspecified); TOW Missiles (590); HIMARS Ammunition (unspecified); HARM Missiles (unspecified) | 9 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18) |  | https://www.defense.gov/News/Releases/Release/Article/3272866/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-01-25 | Ukraine Security Assistance Initiative | Abrams Tanks (31) and Ammunition | 10 | Javelin (11,000+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) | First mention of Abrams tanks in a USAI package. Taiwan is set to receive a different type of Abrams than Ukraine received, so the tank overlap is not as neat of a fit as other capabilities like HIMARS and munitions. | https://www.defense.gov/News/Releases/Release/Article/3277443/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-02-03 | Presidential Drawdown | HIMARS Ammunition (unspecified); Javelin (250) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3287992/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-02-20 | Presidential Drawdown | HIMARS Ammunition (unspecified); Javelin (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31)
2023-02-24 | Ukraine Security Assistance Initiative | HIMARS Ammunition (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) | Noteworthy that HIMARS ammunition is being provided to Ukraine via USAI for the first time. USAI entails the procurement of new capabilities and not drawdowns of existing stockpiles. Meaning that this HIMARS ammunition order directly competes with FMS orders from Taiwan in terms of production of new munitions. | https://www.defense.gov/News/Releases/Release/Article/3308633/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-03-03 | Presidential Drawdown | HIMARS Ammunition (unspecified); | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3318337/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-03-20 | Presidential Drawdown | HIMARS Ammunition (unspecified); HARM Missiles (unspecified); | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3334472/dod-announces-additional-security-assistance-for-ukraine/
2023-04-04 | Presidential Drawdown | Patriot Munitions (unspecified); HIMARS Ammunition (unspecified); TOW Missiles (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3350958/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-04-04 | Ukraine Security Assistance Initiative | NASAMS Munitions; Javelin (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3350958/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-04-19 | Presidential Drawdown | HIMARS Ammunition (unspecified); TOW Missiles (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3367924/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-05-03 | Presidential Drawdown | HIMARS Ammunition (unspecified); TOW Missiles (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3383288/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-05-21 | Presidential Drawdown | HIMARS Ammunition (unspecified); TOW Missiles (unspecified); Javelins (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3402206/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-05-31 | Presidential Drawdown | Patriot Munitions (unspecified); HIMARS Ammunition (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3411804/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-06-09 | Ukraine Security Assistance Initiative | Patriot Munitions (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3422822/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-06-13 | Presidential Drawdown | NASAMS Munitions (unspecified);HIMARS Ammunition (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/News-Stories/Article/Article/3427152/dod-announces-new-round-of-aid-for-ukraine/
2023-06-27 | Presidential Drawdown | Patriot Munitions (unspecified); HIMARS Ammunition (unspecified); TOW Missiles (unspecified); Javelin (unspecified); HARM Missiles (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3440628/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-07-07 | Presidential Drawdown | Patriot Munitions (unspecified); HIMARS Ammunition (unspecified); TOW Missiles (unspecified); Javelin (unspecified) | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (8); HARM Missiles; TOW Missiles (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3451570/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-07-19 | Ukraine Security Assistance Initiative | NASAMS (4) and Munitions; TOW Missiles | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) | First time that TOW Missiles are mentioned in the USAI authority. Taiwan has TOW Missiles on backlog, but they are expected to be delivered in 2024. | https://www.defense.gov/News/Releases/Release/Article/3463890/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-07-25 | Presidential Drawdown | Patriot Munitions; NASAMS Munitions; HIMARS Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3470064/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-08-14 | Presidential Drawdown | Patriot Munitions; HIMARS Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3491937/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-08-29 | Presidential Drawdown | HIMARS Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3509116/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-09-06 | Presidential Drawdown | HIMARS Ammunition; Abrams Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3516840/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-09-07 | Ukraine Security Assistance Initiative | HIMARS Ammunition | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3518903/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-09-21 | Presidential Drawdown | HIMARS Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3534283/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-10-11 | Presidential Drawdown | HIMARS Ammunition; TOW Missiles | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3553644/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-10-26 | Presidential Drawdown | NASAMS Munitions; HIMARS Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3569812/biden-administration-announces-additional-security-assistance-for-ukraine/
2023-11-03 | Presidential Drawdown | NASMS Munitions; HIMARS Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (20 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://defense.gov/News/Releases/Release/Article/3578754/biden-administration-announces-new-security-assistance-for-ukraine/
2023-11-20 | Presidential Drawdown | HIMARS (1) and Ammunition; TOW Missiles; Javelin | 10 | Javelin (11,250+); HIMARS* (21 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3594318/biden-administration-announces-new-security-assistance-for-ukraine/
2024-04-24 | Presidential Drawdown | Stinger; HIMARS Ammunition; Javelin; TOW Missiles | 10 | Javelin (11,250+); HIMARS* (21 PDA, 18 USAI); HIMARS amunition; Harpoon* (2); NASAMS* (12); HARM Missiles; TOW Missiles* (2,590); Patriot Munitions; Paladin Howitzers (18); Abrams Tanks* (31) |  | https://www.defense.gov/News/Releases/Release/Article/3754238/biden-administration-announces-significant-new-security-assistance-for-ukraine/

## Contract Award Announcements
Date of Award | Capability | Related Backlog Item | Other FMS Customers | Date of Completion | FMS Obligated (millions) | Total Contract (Millions) | Source
2024-04-24 | Engine Support for F-15 and F-16 Aircraft | Aircraft Maintenance and Spares | Yes | 2026-03-15 | 1.13 | 13.75
2024-04-19 | E-2C/D Sustainment and Technical Support | Aircraft Maintenance and Spares | Yes | 2025-04-01 | 11.5 | 26.2 | https://www.defense.gov/News/Contracts/Contract/Article/3749216/
2024-03-29 | F-16 CORE Sustainment | Aircraft Maintenance and Spares | Yes | 2025-02-28 | 33.8 | 33.8 | https://www.defense.gov/News/Contracts/Contract/Article/3725457/
2024-03-12 | MQ-9B Procurement | MQ-9B | No | 2027-08-11 | 120 | 250 | https://www.defense.gov/News/Contracts/Contract/Article/3704846/
2024-02-02 | AGM-154 Block III (50) | AGM-154 JSOW | No | 2028-03-01 | 48.8 | 68.4 | https://www.defense.gov/News/Contracts/Contract/Article/3665263/
2024-01-23 | Mission Planning and Support Services | N/A | Yes | 2024-12-31 | N/A | 40 | https://www.defense.gov/News/Contracts/Contract/Article/3653384/
2024-01-11 | Non-Recurring Engineering for Harpoon Coastal Defense System | Harpoon Coastal Defense System | No | 2025-01-01 | 6.9 | 14.1 | https://www.defense.gov/News/Contracts/Contract/Article/3643583/
2023-12-04 | Program Support Services for Utility Helicopters Office | N/A | Yes | 2024-09-30 | 10.6 | 10.6 | https://www.defense.gov/News/Contracts/Contract/Article/3606232/